## Sheet1
Unit 2 Project
Functional Components
| To Do's | In Progress | Completed | Issues |  | Day |  | Deliverable |  | ¦ | Component | ¦ | Priority | ¦ | Est Time (Hrs) | ¦ | Time Invested | ¦ | Actual Time | ¦ | Users Table
[10 empty] | ¦ | --- | ¦ | :---: | ¦ | :---: | ¦ | :---: | ¦ | :---: | ¦ | Serial Key Int | Full Name | Username | Email | Password | Avatar_url
|  | Wireframe |  |  | ¦ | Day 1 Wednesday | ¦ | Wireframes / Priority Matrix | ¦ | ¦ | Database Creation | ¦ | H | ¦ | 1 | ¦ |  | ¦ |  | ¦ | 1 | John Doe | johndope | john.doe@gmail.com | asdfasdf | john.jpg
| Priority Matrix |  |  |  | ¦ | Day 2 Thursday | ¦ | Project Approval / Pseudo Code | ¦ | ¦ | Create User Table | ¦ | H | ¦ | 0.5 | ¦ |  | ¦ |  | ¦ | 2 | Jane Doe | janemane | jane.doe@gmail.com | fdsafasfda | jane.jpg
| Approval |  |  |  | ¦ | Day 3 Friday | ¦ | Basic Clickable Model | ¦ | ¦ | Create Blog Table | ¦ | H | ¦ | 0.5 | ¦ |  | ¦ |  | ¦ | 3 | Alex Smith | asmith | alex.smith@email.com | lfsjvklkvxcx | alex.jpg
[5 empty] | ¦ | Day 4 Saturday | ¦ | Working Prototype | ¦ | ¦ | Create New User - Register New User | ¦ | H | ¦ | 2 | ¦ |  | ¦ |  | ¦ | 4
[5 empty] | ¦ | Day 5 Sunday | ¦ | Final Working Project / MVP | ¦ | ¦ | Read Users - Users Directory | ¦ | H | ¦ | 1 | ¦ |  | ¦ |  | ¦ | 5
[5 empty] | ¦ | Day 6 Monday | ¦ | Bugs / Styling / Post MVP | ¦ | ¦ | Read User Info - Profile Page | ¦ | H | ¦ | 1.5 | ¦ |  | ¦ |  | ¦
[5 empty] | ¦ | Day 7 Tuesday | ¦ | Presentations | ¦ | ¦ | Update User Info | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦ | Entry Table
[10 empty] | ¦ | Delete User - Account Deletion | ¦ | M | ¦ | 0.5 | ¦ |  | ¦ |  | ¦ | Serial Key Int | Title | Content | Image_url | user_id
[10 empty] | ¦ | Create New Blog | ¦ | H | ¦ | 2 | ¦ |  | ¦ |  | ¦ | 1 | Trip to France | "Had an amazing time" | france.jpg | 1
[10 empty] | ¦ | Read Blog - Show All Blog Entries From One User | ¦ | H | ¦ | 2 | ¦ |  | ¦ |  | ¦ | 2 | Trip to Florence | "It was better than I expected" | florence.jpg | 1
[10 empty] | ¦ | Read Blog - Show One Blog Entry From One User | ¦ | H | ¦ | 1 | ¦ |  | ¦ |  | ¦ | 3 | Trip to Italy | "Rome is beautiful" | italy.jpg | 1
| MVP |  |  | PMVP | [5 empty] | ¦ | Update One Blog Entry From One User | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦ | 4 | Belize At Night | "I loved the food" | belize.jpg | 2
| * | User signup |  | * | API integration for displaying visited locations information |  |  |  |  | ¦ | Delete One Blog Entry From One User | ¦ | M | ¦ | 0.5 | ¦ |  | ¦ |  | ¦ | 5 | A Week In Iceland | "The glaciers were amazing" | iceland.jpg | 2
| * | User login |  | * | Design enhancements |  |  |  |  | ¦ | Authentication - Login | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦
| * | User profile with ability to edit or delete account |  | * | Blog commenting functionality |  |  |  |  | ¦ | Authorization - Public - Private Page Access | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦
| * | Display users |  | * | Travel costs or money spent integration |  |  |  |  | ¦ | Flex Box | ¦ | L | ¦ | 0.5 | ¦ |  | ¦ |  | ¦ | Table: | users | Schema |  | entries | Schema
| * | Blog entry creation with ability to edit or delete |  | * | Authorization for selective profile viewing |  |  |  |  | ¦ | Video Presentation | ¦ | L | ¦ | 1 | ¦ |  | ¦ |  | ¦ |  | id | Primary Serial Key |  | id | Primary Serial Key
| * | Display blog entries from a single user | [7 empty] | ¦ | Post MVP: API Integration | ¦ | M | ¦ | 3 | ¦ |  | ¦ |  | ¦ |  | name | VARCHAR(50) |  | title | VARCHAR(225)
| * | Display one blog entry from a single user | [7 empty] | ¦ | Post MVP: Design | ¦ | H | ¦ | 1.5 | ¦ |  | ¦ |  | ¦ |  | username | VARCHAR(50) |  | content | TEXT
| * | Flex Box for page designs | [7 empty] | ¦ | Post MVP: Comments Section | ¦ | L | ¦ | 1.5 | ¦ |  | ¦ |  | ¦ |  | email | VARCHAR(50) |  | image_url | VARCHAR(225)
[10 empty] | ¦ | Post MVP: Selective Blog accessibility | ¦ | L | ¦ | 3 | ¦ |  | ¦ |  | ¦ |  | password | VARCHAR(50) |  | user_id | INT REFERENCES users.id
Relationships tables
Google API Autocompletion | [5 empty] | http://guides.rubyonrails.org/association_basics.html
https://developers.google.com/places/web-service/autocomplete
Place ID finder | [9 empty] | ¦ | Sum Hours | ¦ |  | ¦ | 31 | ¦ |  | ¦ |  | ¦ |  | avatar_url | VARCHAR(225)
https://developers.google.com/places/web-service/place-id
Google API Query samples
https://maps.googleapis.com/maps/api/place/details/json?placeid=ChIJrbS_8-Fv5kcRzSjPvnUT03s
https://maps.googleapis.com/maps/api/geocode/json?components=postal_code%3A00100%7Ccountry%3AIT&key=
https://maps.googleapis.com/maps/api/place/textsearch/json?query=restaurant&location=41.9228369%2C12.5014301&radius=5000&key=
https://maps.googleapis.com/maps/api/place/details/json?placeid=ChIJN1t_tDeuEmsRUsoyG83frY4&key=
Confirmed Query Strings (add key to end)
Query Boilerplate (output?params) | placeid&key= | Place |  |  |  | Additional Links
https://maps.googleapis.com/maps/api/place/details/json?placeid= | ChIJrbS_8-Fv5kcRzSjPvnUT03s&key= | Eiffel Tower |  |  |  | https://uxdesign.cc/stop-calling-these-dark-design-patterns-or-dark-ux-these-are-simply-asshole-designs-bb02df378ba?ref=webdesignernews.com
| ChIJy7cGfBlawokR5l2e93hsoEA&key= | One World Trade Center |  |  |  | https://flexboxfroggy.com/
| ChIJGeGDRsQEdkgRZ6FVAXOU4ds&key= | Big Ben and House of Parliament |  |  |  | https://css-tricks.com/snippets/css/a-guide-to-flexbox/
| ChIJmzrzi9Y0K4gRgXUc3sTY7RU&key= | CN Tower
| ChIJuQ8GvIFOwokRvJcdUIj0Pss&key= | Joe and Pat's Pizzeria