## Sheet1
Unit 2 Project
| Schedule |  |  |  |  | Users Table
| ¦ | Day | ¦ | Deliverable | ¦ | Serial Key Int | Full Name | Username | Email | Password | Avatar_url
| ¦ | --- | ¦ | --- | ¦ | 1 | John Doe | johndope | john.doe@gmail.com | asdfasdf | john.jpg
| ¦ | Day 1 Wednesday | ¦ | Wireframes / Priority Matrix | ¦ | 2 | Jane Doe | janemane | jane.doe@gmail.com | fdsafasfda | jane.jpg
| ¦ | Day 2 Thursday | ¦ | Project Approval / Pseudo Code | ¦ | 3 | Alex Smith | asmith | alex.smith@email.com | lfsjvklkvxcx | alex.jpg
| ¦ | Day 3 Friday | ¦ | Basic Clickable Model | ¦ | 4
| ¦ | Day 4 Saturday | ¦ | Working Prototype | ¦ | 5
| ¦ | Day 5 Sunday | ¦ | Final Working Project / MVP | ¦
| ¦ | Day 6 Monday | ¦ | Bugs / Styling / Post MVP | ¦ | Entry Table
| ¦ | Day 7 Tuesday | ¦ | Presentations | ¦ | Serial Key Int | Title | Content | Image_url | user_id
[6 empty] | 1 | Trip to France | "Had an amazing time" | france.jpg | 1
Relationships tables | [5 empty] | 2 | Trip to Florence | "It was better than I expected" | florence.jpg | 1
http://guides.rubyonrails.org/association_basics.html | [5 empty] | 3 | Trip to Italy | "Rome is beautiful" | italy.jpg | 1
[6 empty] | 4 | Belize At Night | "I loved the food" | belize.jpg | 2
Additional Links | [5 empty] | 5 | A Week In Iceland | "The glaciers were amazing" | iceland.jpg | 2
https://uxdesign.cc/stop-calling-these-dark-design-patterns-or-dark-ux-these-are-simply-asshole-designs-bb02df378ba?ref=webdesignernews.com
https://flexboxfroggy.com/
https://css-tricks.com/snippets/css/a-guide-to-flexbox/ | [5 empty] | Table: | users | Schema |  | entries | Schema
[7 empty] | id | Primary Serial Key |  | id | Primary Serial Key
[7 empty] | name | VARCHAR(50) |  | title | VARCHAR(225)
[7 empty] | username | VARCHAR(50) |  | content | TEXT
[7 empty] | email | VARCHAR(50) |  | image_url | VARCHAR(225)
[7 empty] | password | VARCHAR(50) |  | user_id | INT REFERENCES users.id
[7 empty] | avatar_url | VARCHAR(225)

## Functional Components
Functional Components
¦ | Component | ¦ | Priority | ¦ | Est Time (Hrs) | ¦ | Time Invested (Hrs) | ¦ | Actual Time (Hrs) | ¦
¦ | --- | ¦ | :---: | ¦ | :---: | ¦ | :---: | ¦ | :---: | ¦
¦ | Database Creation | ¦ | H | ¦ | 1 | ¦ | 1 | ¦ | 0.2 | ¦
¦ | Create User Table | ¦ | H | ¦ | 0.5 | ¦ | 0.5 | ¦ | 0.5 | ¦
¦ | Create Blog Table | ¦ | H | ¦ | 0.5 | ¦ |  | ¦ |  | ¦
¦ | Create New User - Register New User | ¦ | H | ¦ | 2 | ¦ | 1 | ¦ | 3 | ¦
¦ | Read Users - Users Directory | ¦ | H | ¦ | 1 | ¦ |  | ¦ | 1 | ¦
¦ | Read User Info - Profile Page | ¦ | H | ¦ | 1.5 | ¦ |  | ¦ | 1 | ¦
¦ | Update User Info | ¦ | M | ¦ | 2 | ¦ | 1 | ¦ |  | ¦
¦ | Delete User - Account Deletion | ¦ | M | ¦ | 0.5 | ¦ |  | ¦ |  | ¦
¦ | Create New Blog Entry | ¦ | H | ¦ | 2 | ¦ |  | ¦ |  | ¦
¦ | Read Blog - Show All Blog Entries From One User | ¦ | H | ¦ | 2 | ¦ |  | ¦ |  | ¦
¦ | Read Blog - Show One Blog Entry From One User | ¦ | H | ¦ | 1 | ¦ |  | ¦ |  | ¦
¦ | Update One Blog Entry From One User | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦
¦ | Delete One Blog Entry From One User | ¦ | M | ¦ | 0.5 | ¦ |  | ¦ |  | ¦
¦ | Authentication - Login | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦
¦ | Authorization - Public - Private Page Access | ¦ | M | ¦ | 2 | ¦ |  | ¦ |  | ¦
¦ | Flex Box | ¦ | L | ¦ | 0.5 | ¦ |  | ¦ |  | ¦
¦ | Video Presentation | ¦ | L | ¦ | 1 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: API Integration - Research | ¦ | M | ¦ | 1 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: API Integration - Planning | ¦ | M | ¦ | 0.5 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: API Integration - Development | ¦ | M | ¦ | 1.5 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: Design | ¦ | H | ¦ | 1.5 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: Comments Section | ¦ | L | ¦ | 1.5 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: Selective Blog accessibility - Planning | ¦ | L | ¦ | 1 | ¦ |  | ¦ |  | ¦
¦ | Post MVP: Selective Blog accessibility - Development | ¦ | L | ¦ | 1 | ¦ |  | ¦ |  | ¦
¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦ |  | ¦
¦ | Sum Hours | ¦ |  | ¦ | 30 | ¦ | 3.5 | ¦ | 5.7 | ¦

## Features
| Basic Clickable Model |  | Working Prototype |  | MVP |  | PMVP
* | Landing page: Login Button, Register New User, Public Directory of Users | * | User signup | * | User signup | * | API integration for displaying visited locations information
* | Public Directory of Users: Gallery of usernames, links to Individual Public Profiles | * | User login | * | User login | * | Design enhancements
* | Individual Public Profiles: Display user's username, email and avatar, sample list of blog entries links to individual public blog entry | * | User profile with ability to edit or delete account | * | User Authentication | * | Blog commenting functionality
* | Individual Public Blog Entry: Input text fields, Post button, Edit Button, Delete Button | * | Display users | * | User profile with ability to edit or delete account | * | Travel costs or money spent integration
|  | * | Blog entry creation with ability to edit or delete | * | Display users | * | Authorization for selective profile viewing
|  | * | Display blog entries from a single user | * | Blog entry creation with ability to edit or delete
|  | * | Display one blog entry from a single user | * | Display blog entries from a single user
|  |  |  | * | Display one blog entry from a single user
|  |  |  | * | Flex Box for page designs

## Google Places
Google API Autocompletion
https://developers.google.com/places/web-service/autocomplete
Place ID finder
https://developers.google.com/places/web-service/place-id
Google API Query samples
https://maps.googleapis.com/maps/api/place/details/json?placeid=ChIJrbS_8-Fv5kcRzSjPvnUT03s
https://maps.googleapis.com/maps/api/geocode/json?components=postal_code%3A00100%7Ccountry%3AIT&key=
https://maps.googleapis.com/maps/api/place/textsearch/json?query=restaurant&location=41.9228369%2C12.5014301&radius=5000&key=
https://maps.googleapis.com/maps/api/place/details/json?placeid=ChIJN1t_tDeuEmsRUsoyG83frY4&key=
Confirmed Query Strings (add key to end)
Query Boilerplate (output?params) | placeid&key= | Place
https://maps.googleapis.com/maps/api/place/details/json?placeid= | ChIJrbS_8-Fv5kcRzSjPvnUT03s&key= | Eiffel Tower
| ChIJy7cGfBlawokR5l2e93hsoEA&key= | One World Trade Center
| ChIJGeGDRsQEdkgRZ6FVAXOU4ds&key= | Big Ben and House of Parliament
| ChIJmzrzi9Y0K4gRgXUc3sTY7RU&key= | CN Tower
| ChIJuQ8GvIFOwokRvJcdUIj0Pss&key= | Joe and Pat's Pizzeria